## Changes
Changes
Legend: yellow cells (Status, Notes) are yours to edit. Everything else is reference text from the review.
# | Area | Problem with the draft | Recommendation | Status | Notes
1 | State model | Liveness, focus and activity are mixed into one state graph, so it can't express "capturing but no longer focused" or "focused but suspect". | Keep three separate fields per session: liveness, last_focus_in timestamp, and activity. Eligible = live, not busy, highest last_focus_in. | Not started
2 | Heartbeats | If one loop both chunks a large capture and answers heartbeats, the client looks hung and flips to Suspect mid-capture. | Answer heartbeats from a separate thread or task, or count chunk progress as liveness. | Not started
3 | Focus handling in the wrapper | The wrapper receives focus sequences on stdin. Leaking them to the shell, or letting a nested cvb register a second client for one terminal, causes bugs. | Pass events through if the child enabled focus reporting, otherwise strip them. Detect nesting with an environment variable and refuse or pass through. | Not started
4 | Protocol machinery | Duplicate delivery can't happen on a Unix stream socket, and Cancelled and Selecting add states nothing uses yet. | Make failure final in v1 (user presses the hotkey again). Drop Cancelled until something can cancel; merge Selecting into Received. | Not started
5 | `cvb capture` behavior | Unspecified. A silently failing hotkey feels broken, and "captured as of when" is undefined. | Block until a terminal state, with a deadline; exit nonzero on failure so the shortcut can show a notification. Snapshot when the client receives the request and record an offset or sequence in the metadata. | Not started
6 | What validation proves | Length and SHA-256 prove the transfer was complete and uncorrupted, not that the capture itself was correct. | Keep them, but don't let "Validating" imply more. Add a hard maximum transcript size. | Not started
7 | Restarts and upgrades | The master can restart (for example after an upgrade) while old wrappers are still running. | Put a protocol version integer in the hello, reject mismatches clearly, and have clients auto-reconnect with backoff, registering as a fresh generation. | Not started

## Decisions
Decisions
Legend: yellow cells (Status, Notes) are yours to edit. Everything else is reference text from the review.
# | Decision | Proposed default (draft) | My take | Status | Notes
1 | Client identity | One client per terminal session | Agreed: one client per wrapper/PTY. Add the nesting guard. | Open
2 | Stale or unknown focus | Reject ambiguous focus rather than guess | Distinguish stale from unknown. Never expire focus by age. Reject only if no client has ever reported focus, or the most recently focused client is dead or suspect; don't fall back to the second most recent. | Open
3 | Transcript retention | Private runtime storage with bounded retention | Agreed: use $XDG_RUNTIME_DIR, directory mode 0700, files 0600, with caps on both count and total bytes. | Open
4 | Control transport | Unix domain socket with framed messages | Agreed. Add a SO_PEERCRED uid check and length-prefixed frames with a maximum size. JSON control messages are fine. | Open
5 | Browser transport | Separate loopback HTTP endpoint with explicit authorization and origin protections | Agreed. Keep the listener a separate code path (or later a separate read-only process) so the browser structurally can't reach control operations. | Open
6 | Clipboard ownership | Policy decision until the protocol is settled | Master writes after commit, but only if the request completes within its deadline and is still the latest. Past the deadline, deliver by notification and API instead. | Open